## Edit List
EDITS TO COST ASSESSMENT REV 02 - WORKING VERSION _8 TO FINAL
TSE Irrigation Storage Tanks and Associated Pipeworks (RFP-027) - Contract QPMO-410-CT-05958
Contractor: SAMA Construction ¦ Engineer: KEO ¦ Cost Consultant: WT Partnership ¦ 01-Oct-2026
Basis of the check |  | Every text cell of _8 read; every figure quoted in a note checked against the cell it describes; every cross-reference, link (812), date and activity ID checked against the 'XER WBS' tab; 1,433 formulas recalculated with no error
Result |  | The figures are right: subtotal SAR 6,823,588.27, Overhead and Profit SAR 341,179.41, total SAR 7,164,767.68, all excluding VAT, unchanged. The mistakes are in the notes: Rev 01 wording left behind, shorthand cross-references, two wrong counts, one note contradicting the quantity it supports, one wrong cell reference in a sensitivity formula, and cover pages without their text boxes
Edits applied |  | 68 edits in the final workbook, listed below; none changes an assessed amount. Sensitivity S8 ('Programme' tab, not included in the assessment) rises from SAR 42,510 to SAR 44,510 and the memo line 'Build-Up Comparison'!G102 from SAR 190,767.59 to SAR 190,767.60
Not applied |  | 3 points need a decision, listed at the end
EDITS APPLIED IN THE FINAL WORKBOOK
Ref | Tab | Cell | Line or item | Type | Text in _8 | Text in the final workbook | Reason | Effect on the assessed total
1 | Build-Up | G41 | 2.5 Method statements and plans | Wording | • Quantity: 12.5 engineer-days for the nine documents the programme requires for this works package (QCD18TSEMOB1050 and 1080 to 1150): tank installation (with the supplier's input), pipe installation and tie-in method statements at 2 days each; HSE, CEMP, quality, execution and mobilisation plans at 1 day each, as extensions of the contract-level plans; the ITP at 1.5 days; each with one resubmission • Project documents for a separate site, not head-office overheads, so priced here and not in the Overhead and Profit ('Assessment' tab, row 20) • The dismantling method statement is inside the Item 3 quotation; submittal administration is 2.4 • Rate: assessed allowance (Riyadh market, Sep-2026) • Prepared 21-Jul to 15-Aug-2026, before the Item 1 site staff start on 22-Aug-2026; the design engineer at 2.1 reviews them, he does not write them | • Quantity: 12.5 engineer-days for the nine documents the programme requires for this works package (QCD18TSEMOB1050 and 1080 to 1150): tank installation (with the supplier's input), pipe installation and tie-in method statements at 2 days each; HSE, CEMP, quality, execution and mobilisation plans at 1 day each, as extensions of the contract-level plans; the ITP at 1.5 days; each with one resubmission • Project documents for a separate site, not head-office overheads, so priced here and not in the Overhead and Profit ('Assessment' tab, row 20) • The dismantling method statement is inside the Item 3 quotation; submittal administration is 2.4 • Rate: assessed allowance (Riyadh market, Sep-2026) • Prepared 21-Jul to 15-Aug-2026, before the Item 1 site staff start on 22-Aug-2026; the design engineer at 2.1 reviews them and does not prepare them | 'he does not write them' reads informally for a file that may reach the Engineer | None
2 | Build-Up | G14 | 1.6 Site office cabin | Consistency | • Site period D1 on the 'Programme' tab, Section 3 (activity QCD18TSEMOB1250, 22-Aug-2026, to activity QCD18TSEDMOB1020, 24-Dec-2026) • Rate: assessed allowance (Riyadh market, Sep-2026) | • Site period D1 on the 'Programme' tab, Section 3: 22-Aug-2026 (activity QCD18TSEMOB1250) to 26-Dec-2026, the assessed end of demobilisation, 127 calendar days; the SAMA Submitted Programme ends on 24-Dec-2026 (activity QCD18TSEDMOB1020) • Rate: assessed allowance (Riyadh market, Sep-2026) | The quantity (4.2 months) is the assessed site period of 127 days to 26-Dec-2026 ('Programme'!H49); the note gave the submitted end date of 24-Dec-2026, which is 125 days, 4.1 months | None
3 | Build-Up | G15 | 1.7 Welfare cabin | Consistency | • Site period D1 on the 'Programme' tab, Section 3 (activity QCD18TSEMOB1250, 22-Aug-2026, to activity QCD18TSEDMOB1020, 24-Dec-2026) • Rate: assessed allowance (Riyadh market, Sep-2026) | • Site period D1 on the 'Programme' tab, Section 3: 22-Aug-2026 (activity QCD18TSEMOB1250) to 26-Dec-2026, the assessed end of demobilisation, 127 calendar days; the SAMA Submitted Programme ends on 24-Dec-2026 (activity QCD18TSEDMOB1020) • Rate: assessed allowance (Riyadh market, Sep-2026) | The quantity (4.2 months) is the assessed site period of 127 days to 26-Dec-2026 ('Programme'!H49); the note gave the submitted end date of 24-Dec-2026, which is 125 days, 4.1 months | None
4 | Build-Up | G16 | 1.8 WC unit | Consistency | • Site period D1 on the 'Programme' tab, Section 3 (activity QCD18TSEMOB1250, 22-Aug-2026, to activity QCD18TSEDMOB1020, 24-Dec-2026) • Rate: assessed allowance (Riyadh market, Sep-2026) | • Site period D1 on the 'Programme' tab, Section 3: 22-Aug-2026 (activity QCD18TSEMOB1250) to 26-Dec-2026, the assessed end of demobilisation, 127 calendar days; the SAMA Submitted Programme ends on 24-Dec-2026 (activity QCD18TSEDMOB1020) • Rate: assessed allowance (Riyadh market, Sep-2026) | The quantity (4.2 months) is the assessed site period of 127 days to 26-Dec-2026 ('Programme'!H49); the note gave the submitted end date of 24-Dec-2026, which is 125 days, 4.1 months | None
5 | Build-Up | G18 | 1.10 Water storage tank | Consistency | • Site period D1 on the 'Programme' tab, Section 3 (activity QCD18TSEMOB1250, 22-Aug-2026, to activity QCD18TSEDMOB1020, 24-Dec-2026) • Rate: assessed allowance (Riyadh market, Sep-2026) | • Site period D1 on the 'Programme' tab, Section 3: 22-Aug-2026 (activity QCD18TSEMOB1250) to 26-Dec-2026, the assessed end of demobilisation, 127 calendar days; the SAMA Submitted Programme ends on 24-Dec-2026 (activity QCD18TSEDMOB1020) • Rate: assessed allowance (Riyadh market, Sep-2026) | The quantity (4.2 months) is the assessed site period of 127 days to 26-Dec-2026 ('Programme'!H49); the note gave the submitted end date of 24-Dec-2026, which is 125 days, 4.1 months | None
6 | Build-Up | G26 | 1.18 PPE | Consistency | • Peak Contractor headcount from the resource matrix ('Programme' tab, Section 4): two helper gangs and the offloading gang (up to 14), five site staff and the pipework crew - about 20 sets; the supplier's crews wear their own • Rate: assessed allowance (Riyadh market, Sep-2026) | • Peak Contractor headcount from the resource bridge ('Programme' tab, Section 4): up to 12 approved helpers in the peak week (W10), five site staff (roles R1 to R5) and the pipework testing crew of 2 - about 20 sets; the supplier's crews wear their own • Rate: assessed allowance (Riyadh market, Sep-2026) | 'Resource matrix' and the gang counts are Rev 01 wording; Rev 02 has the resource bridge, whose peak approved helper deployment is 12 (week W10) | None
7 | Build-Up | G40 | 2.4 Document controller | Figure | • The programme carries 19 deliverable and submittal activities plus the material approval and inspection requests; 8 days of document control, doubled from the previous revision on that evidence • Rate: assessed allowance (Riyadh market, Sep-2026) | • The programme carries 20 deliverable and submittal activities plus the material approval and inspection requests; 8 days of document control, doubled from the previous revision on that evidence • Rate: assessed allowance (Riyadh market, Sep-2026) | The programme has 20 submittal activities, QCD18TSEMOB1040 to 1230 ('XER WBS' tab), not 19 | None
8 | Build-Up | G69 | 4.1 Haulage | Consistency | • 14 loads: bulked debris of one 34 m x 30 m x 4 m tank is about 150-250 m3 loose, i.e. 10-14 loads of a 30 m3 truck • Local haulage SAR 450/load - assumption, to be confirmed with the handover location | • 14 loads: the Contractor's load count, retained; the panels, roof and bracing of one 34 m x 30 m x 4 m tank are about 2,700 m2 of panel, which loose-stacked with the bracing is consistent with 10 to 14 loads of a 30 m3 truck • Local haulage SAR 450/load - assumption, to be confirmed with the handover location | 150 to 250 m3 at 30 m3 a load is 5 to 8 loads, not 10 to 14; the note contradicted the 14 loads it supports | None
9 | Build-Up | G80 | 5.6 Podium steps | Wording | As 5.4. Rate: assessed allowance (Riyadh market, Sep-2026) | • 2 No. for the access window D6 on the 'Programme' tab, Section 3, rounded up to whole hire months • Rate: assessed allowance (Riyadh market, Sep-2026) | 'As 5.4' is shorthand; every basis cell is to be self-contained | None
10 | Build-Up | G84 | 5.10 Helpers | Consistency | • Rate: SAR 150 a day x 26 working days = SAR 3,900 a person-month, the same labourer day rate as every other labour line (1.16, 7.8, 8.18); the programme works 10-hour days, 6 days a week • The approved manpower histogram's helper row, 85 person-weeks, as reproduced week by week on the 'Programme' tab, Section 4, converted to person-days on each week's working days and to person-months at 26 working days; every helper person-day priced once here, so the transfer labour 7.4 is nil and 7.8 carries only the Tank 2 disinfection after the histogram ends • The dismantling-week helpers are priced provisionally (S7) • Skilled people are within Items 3, 6 and 8 on their recorded or described scopes ('Build-Up' Assumption 9) and are not priced • The Contractor's histogram helper row (85 person-weeks) is reconciled week by week there; it is not adopted • The rate is an assessed allowance | • Rate: SAR 150 a day x 26 working days = SAR 3,900 a person-month, the same labourer day rate as every other labour line (1.16, 7.8, 8.18); the programme works 10-hour days, 6 days a week • The approved manpower histogram's helper row, 85 person-weeks, as reproduced week by week on the 'Programme' tab, Section 4, converted to person-days on each week's working days (506 person-days), plus the 9 additional helper person-days assessed in the dated check there (28 to 30-Nov-2026, 3 a day above the approved 3), converted to person-months at 26 working days; every helper person-day priced once here, so the transfer labour 7.4 is nil and 7.8 carries only the Tank 2 disinfection after the histogram ends • The dismantling-week helpers are priced provisionally (S7) • Skilled people are within Items 3, 6 and 8 on their recorded or described scopes ('Build-Up' Assumption 9) and are not priced • The rate is an assessed allowance | The quantity of 19.8 person-months is (506 approved person-days + 9 additional person-days from the dated check) / 26; the basis omitted the 9. The fifth bullet said the helper row 'is not adopted' while the second bullet adopts it | None
11 | Build-Up | G87 | 5.13 Storage consumables | Wording | • Quantity: 2 tanks • The bolts, nuts, washers and tie rods are supplied and fixed by the tank supplier (MNT-AY-486, items 3 and 4; Assumption 9) and are not priced here • Storing the materials until the site is ready and moving them to the installation area are the client's, so the Contractor's (MNT-AY-486 note, page 2): the consumables for that handling are a fair Contractor cost, priced once here; the containers are 1.11 and the plant 5.1 and 5.2. Rate: assessed allowance • Previously 'fixings, touch-up and miscellaneous consumables', 2 tanks at SAR 2,250.00 | • Quantity: 2 tanks • The bolts, nuts, washers and tie rods are supplied and fixed by the tank supplier (MNT-AY-486, items 3 and 4; Assumption 9) and are not priced here • Storing the materials until the site is ready and moving them to the installation area fall to the supplier's client, the Contractor (MNT-AY-486 note, page 2): the consumables for that handling are a fair Contractor cost, priced once here; the containers are 1.11 and the plant 5.1 and 5.2 • Rate: assessed allowance • Previously 'fixings, touch-up and miscellaneous consumables', 2 tanks at SAR 2,250.00 | 'the client's' could be read as the Employer; the quotation's client is the Contractor | None
12 | Build-Up | G106 | 7.5 Top-up water | Wording | Quantity: 10 per cent of the first fill, for losses while the water waits in Tank 1 and for topping Tank 2 up to its test level - Assessed basis. Rate: as 7.1 | • Quantity: 10 per cent of the first fill, for losses while the water waits in Tank 1 and for topping Tank 2 up to its test level - assessed basis • Rate: tankered water at SAR 15.00/m3, the rate at line 7.1 | 'Rate: as 7.1' is shorthand; the rate and its source are stated | None
13 | Build-Up | G125 | 7.24 Tank 1 operating fill | Wording | • Quantity: 34 m x 30 m x 1.0 m = 1,020 m3, an assessed operating depth for the witnessed pumping demonstration from Tank 1 (RFP Scope of Works 5.2, integrated system commissioning) - the Engineer decides the depth; Tank 1 is empty after its test water is pumped to Tank 2 • Filled by tanker on 09 and 10-Dec-2026 while Tank 2 is on its hold ('Programme' tab, window P20b), attended by the approved histogram helpers (duty H11), so no extra labour and no programme effect • A network refill after the tie-in is not assumed: no source, cost or timing has been confirmed by the Employer • If the Engineer requires Tank 1 at full test level for the commissioning, see sensitivity S8 on the 'Programme' tab • Rate: as 7.1; the water source is unconfirmed | • Quantity: 34 m x 30 m x 1.0 m = 1,020 m3, an assessed operating depth for the witnessed pumping demonstration from Tank 1 (RFP Scope of Works 5.2, integrated system commissioning) - the Engineer decides the depth; Tank 1 is empty after its test water is pumped to Tank 2 • Filled by tanker on 09 and 10-Dec-2026 while Tank 2 is on its hold ('Programme' tab, window P20b), attended by the approved histogram helpers (duty H11), so no extra labour and no programme effect • A network refill after the tie-in is not assumed: no source, cost or timing has been confirmed by the Employer • If the Engineer requires Tank 1 at full test level for the commissioning, see sensitivity S8 on the 'Programme' tab • Rate: tankered water at SAR 15.00/m3, the rate at line 7.1; the water source is unconfirmed | 'Rate: as 7.1' is shorthand; the rate and its source are stated | None
14 | Build-Up | G126 | 7.25 Spray disinfection | Consistency | • Quantity: 2 tanks • The chlorinated test water (7.6, 7.7) disinfects only the surfaces it touches, up to the 3.7 m test level; the surfaces above it are not covered by that method and need a separate spray or swab application (AWWA C652 surface-application method) • Tank 2 on 03 and 05-Dec-2026 before the transfer, Tank 1 on 08-Dec after it is emptied • Rate: Assessed basis per tank - 2 people x 2 days, sprayer hire, hypochlorite solution and confined-space attendance; the Contractor's method statement is outstanding • Its labour is outside the histogram helpers, who have no spare people on the days concerned (daily check) | • Quantity: 2 tanks • The chlorinated test water (7.6, 7.7) disinfects only the surfaces it touches, up to the 3.7 m test level; the surfaces above it are not covered by that method and need a separate spray or swab application (AWWA C652 surface-application method) • Tank 2 between the cleaning at 7.26 and the transfer (03 to 05-Dec-2026; 04-Dec is a Friday), Tank 1 on 08-Dec after it is emptied • Rate: Assessed basis per tank - 2 people x 2 days, sprayer hire, hypochlorite solution and confined-space attendance; the Contractor's method statement is outstanding • Its labour is priced here, outside the histogram helpers: the spare approved people on those days (daily check: 2 on 03-Dec, none on 05-Dec, 1 on 08-Dec) do not cover it | Cleaning (7.26) and spraying were both dated 03 and 05-Dec for Tank 2 although the cleaning comes first; and the daily check shows 2 spare approved helpers on 03-Dec and 1 on 08-Dec, so 'no spare people' was not accurate | None
15 | Build-Up | G127 | 7.26 Interior cleaning | Consistency | • Quantity: 2 tanks • AWWA C652 starts with a clean interior; erection debris, dust and sealant residue are removed before the water is dosed • Rate: 2 people x 2 days at SAR 150 (SAR 600), pressure washer 2 days at SAR 500 (SAR 1,000), wash water 12 m3 at SAR 15 as line 7.1 (SAR 180) - assessed allowance; the Contractor's method statement is outstanding • Tank 1 after the roof closes (12 to 16-Nov), Tank 2 after its nozzles (03 and 05-Dec); labour outside the histogram helpers | • Quantity: 2 tanks • AWWA C652 starts with a clean interior; erection debris, dust and sealant residue are removed before the water is dosed • Rate: 2 people x 2 days at SAR 150 (SAR 600), pressure washer 2 days at SAR 500 (SAR 1,000), wash water 12 m3 at SAR 15 as line 7.1 (SAR 180) - assessed allowance; the Contractor's method statement is outstanding • Tank 1 after the roof closes (12 to 16-Nov); Tank 2 between the end of its mechanical works (03-Dec) and the transfer (05-Dec), ahead of the spray at 7.25; labour outside the histogram helpers | Tank 2 cleaning was dated on the same two days as the spray it precedes | None
16 | Build-Up | A168 | Assumption 2 | Consistency | 2. Rates marked 'assumption' are assessed Riyadh market rates (Sep-2026): crane 50 t SAR 2,500/day; boom truck SAR 1,200/day and telehandler SAR 900/day, both with operator and fuel; scaffolding SAR 55/m2; generator 100 kVA SAR 11,000/month with fuel; general labour SAR 150/day (helpers SAR 3,900 per person-month at 26 working days); rigger SAR 250/day; site engineer SAR 12,000/month; HSE and QA/QC SAR 10,000/month; foreman SAR 8,000/month; test water SAR 15.00/m3 tankered (one 30 m3 load at the local haulage rate); site water SAR 350 per 10 m3 delivery; generator 30 kVA SAR 8,571/month continuous with fuel (hire SAR 4,000 plus diesel at SAR 1.79 a litre); local haulage SAR 450/load; HDPE PE100 pipe 355 mm outside diameter supplied and installed SAR 280/m; gate valve DN300 SAR 6,500; motorised butterfly valve DN355 as listed SAR 14,000 excluding power and control. | 2. Rates marked 'assessed allowance' or 'assumption' are assessed Riyadh market rates (Sep-2026): crane 50 t SAR 2,500/day; boom truck SAR 1,200/day and telehandler SAR 900/day, both with operator and fuel; scaffolding SAR 55/m2; generator 100 kVA SAR 11,000/month with fuel; general labour SAR 150/day (helpers SAR 3,900 per person-month at 26 working days); rigger SAR 250/day; site engineer SAR 12,000/month; HSE and QA/QC SAR 10,000/month; foreman SAR 8,000/month; test water SAR 15.00/m3 tankered (one 30 m3 load at the local haulage rate); site water SAR 350 per 10 m3 delivery; generator 30 kVA SAR 8,571/month continuous with fuel (hire SAR 4,000 plus diesel at SAR 1.79 a litre); local haulage SAR 450/load; HDPE PE100 pipe 355 mm outside diameter supplied and installed SAR 280/m; gate valve DN300 SAR 6,500; motorised butterfly valve DN355 as listed SAR 14,000 excluding power and control. | No line is marked 'assumption'; the lines say 'assessed allowance' | None
17 | Build-Up | A175 | Assumption 9 | Wording | 9. Tank supplier scope - user-authorised assumption. The split of work between the tank supplier and the Contractor is taken as described in the Al Muhaideb National Tanks (National Factory for Fiberglass) quotation MNT-AY-486 dated 24-Jun-2026 with its tank and foundation drawings dated 06-May-2026, received 30-Sep-2026. Included by the supplier (page 1, 'Supply, Installation and Testing'; specifications 1 to 13): manufacture, installation and testing, the non-toxic leak sealant (item 6), all internal bolts, nuts, washers and tie rods in stainless steel 316 and external fixings in hot-dip galvanised steel (items 3 and 4), level indicator tube, screened air vent, lockable manhole, internal and external ladders, roof panel supports, inlet, outlet, overflow and drain openings and the galvanised steel skid base (items 5 to 13). Excluded by the supplier and therefore the Contractor's (exclusions 1 to 6, pages 1 and 2): civil works and foundations; power for the installation; helpers and labourers; unloading and shifting of material at the installation location; all pipe connections, piping, float switches, fittings, flanges, valves, water for testing and any third-party testing or inspection; forklift, crane, elevator and scaffolding if required. The client stores the materials until the site is ready and transports them to the installation area by its own means (note, page 2). Mismatch stated plainly: this is not the adopted Al Mousa S04488 / Stalwart offer. It is a different supplier, a different tank (3,000 m3 gross, 30 (15+15) m x 25 m x 4 m, 3 No., non-insulated, with partition), addressed to WTB, dated June 2026 with 15 days' validity, priced at SAR 1,575,000 per tank net of the discount, VAT excluded (SAR 525 per gross m3). Its price is not adopted; its scope split is applied on instruction as the assessment assumption for Items 5, 6, 7 and 8 until the Al Mousa offer and its conditions are produced ('Build-Up Comparison' tab, Section 7, item 14). | 9. Tank supplier scope - assessment assumption. The split of work between the tank supplier and the Contractor is taken as described in the Al Muhaideb National Tanks (National Factory for Fiberglass) quotation MNT-AY-486 dated 24-Jun-2026 with its tank and foundation drawings dated 06-May-2026, received 30-Sep-2026. Included by the supplier (page 1, 'Supply, Installation and Testing'; specifications 1 to 13): manufacture, installation and testing, the non-toxic leak sealant (item 6), all internal bolts, nuts, washers and tie rods in stainless steel 316 and external fixings in hot-dip galvanised steel (items 3 and 4), level indicator tube, screened air vent, lockable manhole, internal and external ladders, roof panel supports, inlet, outlet, overflow and drain openings and the galvanised steel skid base (items 5 to 13). Excluded by the supplier and therefore the Contractor's (exclusions 1 to 6, pages 1 and 2): civil works and foundations; power for the installation; helpers and labourers; unloading and shifting of material at the installation location; all pipe connections, piping, float switches, fittings, flanges, valves, water for testing and any third-party testing or inspection; forklift, crane, elevator and scaffolding if required. The supplier's client, the Contractor, stores the materials until the site is ready and transports them to the installation area by its own means (note, page 2). This is not the adopted Al Mousa S04488 / Stalwart offer. It is a different supplier, a different tank (3,000 m3 gross, 30 (15+15) m x 25 m x 4 m, 3 No., non-insulated, with partition), addressed to WTB, dated June 2026 with 15 days' validity, priced at SAR 1,575,000 per tank net of the discount, VAT excluded (SAR 525 per gross m3). Its price is not adopted; its scope split is applied as the assessment assumption for Items 5, 6, 7 and 8 until the Al Mousa offer and its conditions are produced ('Build-Up Comparison' tab, Section 7, item 14). | 'user-authorised', 'on instruction' and 'Mismatch stated plainly' are the author talking to himself; 'the client' could be read as the Employer | None
18 | Build-Up Comparison | H45 | Item 5, line 5.6 comment | Consistency | Assessed as power-tool hire, jointing and general consumables ('Build-Up' 5.11 to 5.13). No basis stated. | Assessed as the helpers' power and hand tools and the storage and handling consumables ('Build-Up' 5.11 and 5.13); sealant tools and jointing consumables are within the supplier's price ('Build-Up' 5.12, nil). No basis stated. | Line 5.12 (sealant tools and jointing consumables) is nil in Rev 02 and 5.13 is storage and handling consumables; 'jointing' is Rev 01 wording | None
19 | Build-Up Comparison | H54 | Item 7, line 7.1 comment | Consistency | • Assessed as one fill with transfer to the second tank, interior cleaning, disinfection of the wetted surfaces and of the surfaces above the test water line, flushing, water-quality testing and standby ('Build-Up' 7.1 to 7.12, 7.22, 7.23, 7.25 and 7.26) • Re-testing is the Contractor's obligation and is not allowed • No volume, source or rate stated | • Assessed as one fill with transfer to the second tank, interior cleaning, disinfection of the wetted surfaces and of the surfaces above the test water line, dechlorination, water-quality testing and standby ('Build-Up' 7.1 to 7.12, 7.22, 7.23, 7.25 and 7.26) • Re-testing is the Contractor's obligation and is not allowed • No volume, source or rate stated | There is no flushing line in Item 7; line 7.9 is dechlorination | None
20 | Build-Up Comparison | H69 | Item 8, line 8.6 comment | Figure | Assessed as 260 m of colour banding and 70 tags ('Build-Up' 8.20 and 8.21). No lengths or counts stated. | Assessed as 260 m of colour banding and 97 tags ('Build-Up' 8.20 and 8.21). No lengths or counts stated. | Line 8.21 is 97 tags in Rev 02 (one every 3 m plus one at each valve); 70 is the Rev 01 count | None
21 | Build-Up Comparison | H98 | Section 8, Item 1 note | Figure | • Equals Item 1 x 1.05 exactly • Site establishment and welfare are loaded on the 5-day mobilisation activities (22 to 26-Aug-2026), so the Contractor will apply for the whole of Item 1 except SAR 50,000.00 on mobilisation | • Equals Item 1 x 1.05 exactly • SAR 578,547.85 of the SAR 714,000.00 is loaded on the two 5-day mobilisation activities (22 to 26-Aug-2026), SAR 85,452.15 on the submittal activities and SAR 50,000.00 on demobilisation, so the Contractor will apply for most of Item 1 in the first week on site | The cost loading on the 'XER WBS' tab is SAR 578,547.85 on the two mobilisation activities, SAR 85,452.15 on the submittals and SAR 50,000.00 on demobilisation; the note said the whole item except SAR 50,000.00 was on mobilisation | None
22 | Build-Up Comparison | F102 | Section 8, Item 7 loaded amount | Figure | 200305.97 | 200305.98 | The two testing activities on the 'XER WBS' tab are SAR 100,152.99 each, SAR 200,305.98; G102 recalculates to SAR 190,767.60 | None - memo line in Section 8, not in the assessment
23 | Build-Up Comparison | A73 | Section 7 introduction | Consistency | The substantiation request was issued by WT Partnership to the Contractor via Aconex on 25-Aug-2026 under Sub-Clauses 13.3.1 and 12.3.2 of the Conditions of Contract. A follow-up clarification request was prepared after the Engineer's (KEO) email of 30-Aug-2026; its issue is to be confirmed before it is relied on. | The substantiation request was issued by WT Partnership to the Contractor via Aconex on 25-Aug-2026 under Sub-Clauses 13.3.1 and 12.3.2 of the Conditions of Contract. | The follow-up request is no longer cited in the table (C76:C78 were corrected in _8); the sentence left an 'issue to be confirmed' statement about the file's own content | None
24 | Build-Up Comparison | C76 | Section 7, item 2 | Wording | WT Partnership Aconex substantiation request dated 25-Aug-2026. | WT Partnership Aconex substantiation request dated 25-Aug-2026 | Trailing full stop; C75 has none | None
25 | Build-Up Comparison | C77 | Section 7, item 3 | Wording | WT Partnership Aconex substantiation request dated 25-Aug-2026. | WT Partnership Aconex substantiation request dated 25-Aug-2026 | Trailing full stop; C75 has none | None
26 | Build-Up Comparison | C78 | Section 7, item 4 | Wording | WT Partnership Aconex substantiation request dated 25-Aug-2026. | WT Partnership Aconex substantiation request dated 25-Aug-2026 | Trailing full stop; C75 has none | None
27 | Build-Up Comparison | C79:C91 | Section 7, items 5 to 17 | Wording | This assessment. | This assessment | Trailing full stop; C75 has none | None
28 | Build-Up Comparison | A115 | Section 8, histogram note | Consistency | Direct manpower histogram as submitted (same workbook, sheet 'MP-HST-WK'): 16 weeks of labour on site, week ending 28-Aug to week ending 11-Dec-2026; 221 person-weeks in total, 136 skilled and 85 helpers; peak 35 in the week ending 30-Oct-2026 when the Tank 1 walls and bracing overlap the Tank 2 base. The workbook does not say whose labour it is. The tank supplier's price under Item 6 includes installation and requires 4 to 6 helpers from the Contractor; if the histogram includes the supplier's erection crews it cannot support the Contractor's Items 1, 5 or 7, and if it is the Contractor's own labour, 136 skilled person-weeks on a job whose erection is subcontracted are unexplained. Until the Contractor answers (Section 7, item 10), the histogram is used only as evidence of the 16-week labour window, which sits inside the works period allowed. | Direct manpower histogram as submitted (same workbook, sheet 'MP-HST-WK'): 16 weeks of labour on site, week ending 28-Aug to week ending 11-Dec-2026; 221 person-weeks in total, 136 skilled and 85 helpers; peak 35 in the week ending 30-Oct-2026 when the Tank 1 walls and bracing overlap the Tank 2 base. The workbook does not say whose labour it is. The tank supplier's price under Item 6 includes installation and requires 4 to 6 helpers from the Contractor; if the histogram includes the supplier's erection crews it cannot support the Contractor's Items 1, 5 or 7, and if it is the Contractor's own labour, 136 skilled person-weeks on a job whose erection is subcontracted are unexplained. Until the Contractor answers (Section 7, item 10), the skilled rows are not priced (their work sits within Items 3, 6 and 8) and the helper row is priced once at 'Build-Up' line 5.10 ('Programme' tab, Section 4); the histogram also fixes the 16-week labour window, which sits inside the works period allowed. | The last sentence said the histogram is used only as evidence of the labour window; Rev 02 prices its helper row at 'Build-Up' 5.10 | None
29 | Programme | A8 | Section 1, Instruction | Wording | Instruction • SAMA has been instructed to proceed and is on site (existing tank dismantled; Tank 1 base panels being received). Reference and date not yet supplied; to be recorded on 'Project Info'. • The instruction affects entitlement and certification, not the assessed value. | Instruction • SAMA has been instructed to proceed and is on site (existing tank dismantled; Tank 1 base panels being received). Reference and date not yet supplied. • The instruction affects entitlement and certification, not the assessed value. | 'to be recorded on Project Info' is a note to the author; the tab has no field for it | None
30 | Programme | I47 | P23 Demobilisation | Wording | • Activities QCD18TSEDMOB1020 and QCD18TSEDMOB3020, 17 to 24-Dec-2026, 7 working days in parallel • B follows the completion of testing (P22) | • Activities QCD18TSEDMOB1020 and QCD18TSEDMOB3020, 17 to 24-Dec-2026, 7 working days in parallel • Assessed basis: demobilisation follows the completion of testing (P22), 19 to 26-Dec-2026 | 'B follows' is a leftover label; the bullet names what follows what | None
31 | Programme | I49 | D1 Site period | Wording | • The continuous site establishment runs for this period: welfare cabins, WC, water tank and deliveries, the 30 kVA welfare generator, the site pick-up, workforce transport, the two watchmen and the weekly waste removal, and the site staff whose duties cover the demobilisation week (Section 4, roles) • SAMA Submitted Programme: the SAMA Submitted Programme, 22-Aug to 24-Dec-2026 • Assessment allowance: the same erection dates with the sequential testing fitted in, conditional on the early Tank 1 test (P18) • The site engineer's 3 close-out days at 'Build-Up' line 1.22 fall after this period and are intentionally off-site visits, not a second allowance | • The continuous site establishment runs for this period: welfare cabins, WC, water tank and deliveries, the 30 kVA welfare generator, the site pick-up, workforce transport, the two watchmen and the weekly waste removal, and the site staff whose duties cover the demobilisation week (Section 4, roles) • SAMA Submitted Programme: 22-Aug to 24-Dec-2026 • Assessment allowance: the same erection dates with the sequential testing fitted in, conditional on the early Tank 1 test (P18) • The site engineer's 3 close-out days at 'Build-Up' line 1.22 fall after this period and are intentionally off-site visits, not a second allowance | Repeated phrase 'SAMA Submitted Programme: the SAMA Submitted Programme' | None
32 | Programme | J198 | 7.22 Standby | Wording | • Pump and hose set standing by through the two 24-hour holds and two days of contingency between the Tank 1 test and the transfer; tankers are working, not standing by, during the fill • The same on A, where two simultaneous fills need the same standby | • Pump and hose set standing by through the two 24-hour holds and two days of contingency between the Tank 1 test and the transfer; tankers are working, not standing by, during the fill • The same on the SAMA Submitted Programme, where two simultaneous fills need the same standby | 'The same on A' is a leftover label for the SAMA Submitted Programme column | None
33 | Programme | J68 | W4 note | Wording | • Skilled: tank erection crew, within Item 6 (recorded scope) • Helpers: panel handling Counted: QCD18TSECONT1INS1020 | • Skilled: tank erection crew, within Item 6 (recorded scope) • Helpers: panel handling • Counted: QCD18TSECONT1INS1020 | 'Counted:' ran on from the previous sentence without a separator | None
34 | Programme | J69 | W5 note | Wording | As above Counted: QCD18TSECONT1INS1020 | • Skilled: tank erection crew, within Item 6 (recorded scope) • Helpers: panel handling • Counted: QCD18TSECONT1INS1020 | 'As above' is shorthand; the note is repeated in full | None
35 | Programme | J70 | W6 note | Wording | As above Counted: QCD18TSECONT1INS1020 | • Skilled: tank erection crew, within Item 6 (recorded scope) • Helpers: panel handling • Counted: QCD18TSECONT1INS1020 | 'As above' is shorthand; the note is repeated in full | None
36 | Programme | J71 | W7 note | Wording | As above; helpers offload the wall-panel batches within the same days Counted: QCD18TSECONT1INS1020, QCD18TSECONT1INS1030, QCD18TSECONT1INS1060 | • Skilled: tank erection crew, within Item 6 (recorded scope) • Helpers: panel handling; the helpers offload the wall-panel batches within the same days • Counted: QCD18TSECONT1INS1020, QCD18TSECONT1INS1030, QCD18TSECONT1INS1060 | 'As above' is shorthand; the note is repeated in full | None
37 | Programme | J72 | W8 note | Wording | As above Counted: QCD18TSECONT1INS1030, QCD18TSECONT1INS1060 | • Skilled: tank erection crew, within Item 6 (recorded scope) • Helpers: panel handling • Counted: QCD18TSECONT1INS1030, QCD18TSECONT1INS1060 | 'As above' is shorthand; the note is repeated in full | None
38 | Programme | J73 | W9 note | Wording | • Skilled: erection crews, Item 6 • Helpers: Tank 1 front plus offloading and the Tank 2 base Counted: QCD18TSECONT1INS1030, QCD18TSECONT1INS1060, QCD18TSECONT2INS1020 | • Skilled: erection crews, Item 6 • Helpers: Tank 1 front plus offloading and the Tank 2 base • Counted: QCD18TSECONT1INS1030, QCD18TSECONT1INS1060, QCD18TSECONT2INS1020 | 'Counted:' ran on from the previous sentence without a separator | None
39 | Programme | J74 | W10 note | Wording | • Skilled: two erection crews, Item 6 • Helpers: two gangs Counted: QCD18TSECONT1INS1030, QCD18TSECONT1INS1060, QCD18TSECONT2INS1020, QCD18TSECONT2INS1030 | • Skilled: two erection crews, Item 6 • Helpers: two gangs • Counted: QCD18TSECONT1INS1030, QCD18TSECONT1INS1060, QCD18TSECONT2INS1020, QCD18TSECONT2INS1030 | 'Counted:' ran on from the previous sentence without a separator | None
40 | Programme | J75 | W11 note | Wording | As above Counted: QCD18TSECONT2INS1030, QCD18TSECONT1INS1040, QCD18TSECONT2INS1060, QCD18TSECONT1INS1050 | • Skilled: two erection crews, Item 6 • Helpers: two gangs • Counted: QCD18TSECONT2INS1030, QCD18TSECONT1INS1040, QCD18TSECONT2INS1060, QCD18TSECONT1INS1050 | 'As above' is shorthand; the note is repeated in full | None
41 | Programme | J76 | W12 note | Wording | • Skilled: erection crews (Item 6) and, from 12-Nov, pipework fitters (Item 8 rates) - split unresolved, both priced elsewhere • Helpers: two gangs, pipe offloading Counted: QCD18TSECONT2INS1030, QCD18TSECONT2INS1060, QCD18TSECONT1INS1050 | • Skilled: erection crews (Item 6) and, from 12-Nov, pipework fitters (Item 8 rates) - split unresolved, both priced elsewhere • Helpers: two gangs, pipe offloading • Counted: QCD18TSECONT2INS1030, QCD18TSECONT2INS1060, QCD18TSECONT1INS1050 | 'Counted:' ran on from the previous sentence without a separator | None
42 | Programme | J77 | W13 note | Wording | • Skilled: erection crew (Item 6) or fitters (Item 8) - unresolved, both priced elsewhere • Helpers: Tank 2 gang; Tank 1 fill attendance Counted: QCD18TSECONT2INS1060, QCD18TSECONT2INS1040 | • Skilled: erection crew (Item 6) or fitters (Item 8) - unresolved, both priced elsewhere • Helpers: Tank 2 gang; Tank 1 fill attendance • Counted: QCD18TSECONT2INS1060, QCD18TSECONT2INS1040 | 'Counted:' ran on from the previous sentence without a separator | None
43 | Programme | J78 | W14 note | Wording | As above Counted: QCD18TSECONT2INS1040, QCD18TSECONT2INS1050 | • Skilled: erection crew (Item 6) or fitters (Item 8) - unresolved, both priced elsewhere • Helpers: Tank 2 gang; Tank 1 fill attendance • Counted: QCD18TSECONT2INS1040, QCD18TSECONT2INS1050 | 'As above' is shorthand; the note is repeated in full | None
44 | Programme | J79 | W15 note | Wording | • Skilled: nozzle fitters (Item 6) and pipework (Item 8) - unresolved, both priced elsewhere • Helpers: nozzle attendance; Tank 1 disinfection Counted: QCD18TSECONT2INS1050 | • Skilled: nozzle fitters (Item 6) and pipework (Item 8) - unresolved, both priced elsewhere • Helpers: nozzle attendance; Tank 1 disinfection • Counted: QCD18TSECONT2INS1050 | 'Counted:' ran on from the previous sentence without a separator | None
45 | Programme | J139 | K4 basis | Wording | As K3 | The supplier installs (Assumption 9); provisional until the Al Mousa offer is produced | 'As K3' is shorthand; the note is repeated in full | None
46 | Programme | J141 | K6 basis | Wording | As K5 | Split between Items 6 and 8 unresolved; both prices include their own labour, so nothing extra either way | 'As K5' is shorthand; the note is repeated in full | None
47 | Programme | J181 | 5.6 source | Wording | As 5.4 | 2 No. podium steps for the access window D6, rounded up to whole hire months | 'As 5.4' is shorthand; the note is repeated in full | None
48 | Programme | C232 | 1.18 register | Consistency | Site service - peak Contractor headcount (matrix M3, M5, M9, R1 to R5) | Site service - peak Contractor headcount (Section 4: the peak approved helpers, roles R1 to R5 and the pipework testing crew) | 'matrix M3, M5, M9' are Rev 01 codes that no longer exist | None
49 | Programme | I244 | 3.1 register | Consistency | No - haulage is 4.1; crane and crew within the quotation on its recorded scope (offer not attached), so no plant at Item 5; matrix M2 carries Contractor attendance only | No - haulage is 4.1; crane and crew within the quotation on its recorded scope (offer not attached), so no plant at Item 5; Section 4 (weeks W1 to W3) carries the Contractor's helper attendance only, priced provisionally at 5.10 (S7) | 'matrix M2' is a Rev 01 code that no longer exists | None
50 | Programme | I311 | 8.18 register | Consistency | No - not in 5.10 (matrix M14) | No - the pipework testing crew is not within the helper row priced at 5.10 | 'matrix M14' is a Rev 01 code that no longer exists | None
51 | Programme | B205 | Sensitivities heading | Consistency | Sensitivities on the resource matrix - not included in the assessment | Sensitivities on the resource bridge - not included in the assessment | 'resource matrix' is Rev 01 wording; Section 4 is the resource bridge | None
52 | Programme | C242 | 2.4 register | Figure | QCD18TSEMOB1040 to QCD18TSEMOB1230 (19 submittal activities) and the MAR / MIR activities | QCD18TSEMOB1040 to QCD18TSEMOB1230 (20 submittal activities) and the MAR / MIR activities | 20 submittal activities, not 19 ('XER WBS' tab, QCD18TSEMOB1040 to 1230) | None
53 | Programme | C291 | 7.25 register | Consistency | Tank 2 on 03 and 05-Dec (before P19), Tank 1 on 08-Dec (after P19) | Tank 2 between the cleaning at 7.26 and the transfer (03 to 05-Dec, before P19), Tank 1 on 08-Dec (after P19) | Aligned with the corrected sequence at 'Build-Up' 7.25 and 7.26 | None
54 | Programme | I208 | S8 sensitivity | Formula | =ROUND(G208*D208,2)+4*'Build-Up'!E124+8*'Build-Up'!E24 | =ROUND(G208*D208,2)+4*'Build-Up'!E123+8*'Build-Up'!E24 | The pump standby term referenced 'Build-Up'!E124 (line 7.23, rate nil) instead of E123 (line 7.22, SAR 500 a day); S8 rises from SAR 42,510 to SAR 44,510. Not included in the assessment | None - sensitivity S8 only, not included in the assessment
55 | Programme | C294 | C294 register activities | Wording | As 8.1 | QCD18TSEPRC1160 to 1250 (procurement), QCD18TSECONT1MW2055 and QCD18TSECONT2MW2020 (installation) | 'As 8.1' is shorthand; the activities are repeated in full | None
56 | Programme | C295 | C295 register activities | Wording | As 8.1 | QCD18TSEPRC1160 to 1250 (procurement), QCD18TSECONT1MW2055 and QCD18TSECONT2MW2020 (installation) | 'As 8.1' is shorthand; the activities are repeated in full | None
57 | Programme | C296 | C296 register activities | Wording | As 8.1 | QCD18TSEPRC1160 to 1250 (procurement), QCD18TSECONT1MW2055 and QCD18TSECONT2MW2020 (installation) | 'As 8.1' is shorthand; the activities are repeated in full | None
58 | Programme | C298 | C298 register activities | Wording | As 8.1 | QCD18TSEPRC1160 to 1250 (procurement), QCD18TSECONT1MW2055 and QCD18TSECONT2MW2020 (installation) | 'As 8.1' is shorthand; the activities are repeated in full | None
59 | Programme | C299 | C299 register activities | Wording | As 8.1 | QCD18TSEPRC1160 to 1250 (procurement), QCD18TSECONT1MW2055 and QCD18TSECONT2MW2020 (installation) | 'As 8.1' is shorthand; the activities are repeated in full | None
60 | Programme | C300 | C300 register activities | Wording | As 8.1 | QCD18TSEPRC1160 to 1250 (procurement), QCD18TSECONT1MW2055 and QCD18TSECONT2MW2020 (installation) | 'As 8.1' is shorthand; the activities are repeated in full | None
61 | Programme | C313 | C313 register activities | Wording | As 8.1 | QCD18TSEPRC1160 to 1250 (procurement), QCD18TSECONT1MW2055 and QCD18TSECONT2MW2020 (installation) | 'As 8.1' is shorthand; the activities are repeated in full | None
62 | Programme | C314 | C314 register activities | Wording | As 8.1 | QCD18TSEPRC1160 to 1250 (procurement), QCD18TSECONT1MW2055 and QCD18TSECONT2MW2020 (installation) | 'As 8.1' is shorthand; the activities are repeated in full | None
63 | Programme | C302 | C302 register activities | Wording | As 8.9 | QCD18TSECONT1MW2060 and QCD18TSECONT2MW2040 | 'As 8.9' is shorthand; the activities are repeated in full | None
64 | Programme | C303 | C303 register activities | Wording | As 8.9 | QCD18TSECONT1MW2060 and QCD18TSECONT2MW2040 | 'As 8.9' is shorthand; the activities are repeated in full | None
65 | Programme | C310 | C310 register activities | Wording | As 8.16 | After QCD18TSECONT2MW2020, before P21 | 'As 8.16' is shorthand; the activities are repeated in full | None
66 | Programme | C311 | C311 register activities | Wording | As 8.16 | After QCD18TSECONT2MW2020, before P21 | 'As 8.16' is shorthand; the activities are repeated in full | None
67 | Programme | C312 | C312 register activities | Wording | As 8.16 | After QCD18TSECONT2MW2020, before P21 | 'As 8.16' is shorthand; the activities are repeated in full | None
68 | Cover and Appendix Cover | text boxes | Cover pages | Cover | Brand image only | Text boxes added, linked to 'Project Info' (project name, client, address, contract reference, document subtitle, reference; appendix title, description, reference) | 'Project Info'!B4 says the cover tabs display the Project Info values; both tabs carried the brand image only | None
NOT APPLIED - DECISIONS REQUIRED
Ref | Point |  |  |  | What was found |  | Decision | Who
D1 | 'Approved' manpower histogram |  |  |  | 23 cells call the histogram 'approved' (Assessment L14, A23, A24; 'Build-Up' A73, B84, G84; 'Programme' Section 4 headings and notes); 'Build-Up Comparison'!H78 records the histogram as received 29-Sep-2026 and under the Engineer's approval. Confirm which is right; if it is not approved, 'approved' becomes 'submitted' throughout |  | To be decided | Alaa
D2 | Item 6 price |  |  |  | Item 6 remains at the insulated price, SAR 5,527,000 (81 per cent of the subtotal); a non-insulated price is awaited from the Contractor |  | To be decided | WTP to SAMA
D3 | Revision date |  |  |  | Every tab header and 'Project Info'!C14 carry Rev 02, 30-Sep-2026; if the file is issued after these edits, keep the date or re-date it |  | To be decided | Alaa